## Dev Support
Date | Issue Description | How it is Solved | Team Members Involved | Comments
2026-02-16 | API gateway returning 502 errors intermittently on /auth endpoint | Identified stale connection pool settings; increased timeout and added health-check retry logic. | Alice Chen, Bob Martinez | Happened 3x before root cause found; added alerting.
2026-02-17 | CI/CD pipeline failing on Docker build step — out of disk space on runner | Pruned unused Docker images and volumes via cron job; upgraded runner disk to 100GB. | Bob Martinez | Recurring issue — monitor disk usage weekly.
2026-02-18 | Database migration script timed out on production (10M rows table) | Split migration into batches of 50k rows, ran during off-peak hours with progress logging. | Alice Chen, Carlos Rivera | Migration completed in 4 hours total.
2026-02-19 | OAuth token refresh silently failing for enterprise SSO tenants | Bug in JWT claims parsing — fixed regex for tenant ID extraction and deployed hotfix v2.4.1. | Diana Lee, Alice Chen | Affected ~12 enterprise accounts; all confirmed resolved.
2026-02-20 | Slow dashboard load times (8–12s) reported by multiple users | Added Redis caching for dashboard aggregation queries; load time dropped to ~400ms. | Carlos Rivera, Ethan Kim | Cache invalidation set to 5 min; monitor hit rates.
2026-02-21 | Webhook delivery failures to customer endpoints — TLS handshake errors | Updated outbound TLS to v1.3 only; old customer endpoints on TLS 1.0 need upgrading. | Diana Lee | Notified 3 customers still on TLS 1.0 to upgrade by Mar 1.
2026-02-10 | Redis cluster failover caused 90-second outage | Switched to async replication; reduced failover time to <5s. | Bob Martinez, Carlos Rivera | Post-mortem written; runbook updated.
2026-02-12 | Scheduled job sending duplicate email notifications | Fixed idempotency key logic in job scheduler. | Alice Chen
2026-02-24 | Memory leak detected in WebSocket connection handler |  | Ethan Kim | Under investigation — no fix yet.

## US Support
Date | Issue Description | How it is Solved | Team Members Involved | Comments
2026-02-16 | Customer unable to export reports as PDF — blank pages generated | Traced to wkhtmltopdf timeout for large reports; increased timeout and added pagination. | Fiona Walsh, George Tan | Affected customers with >500 row reports.
2026-02-17 | Wrong timezone shown on scheduled report emails (UTC vs EST) | Added user timezone preference to email service; defaulting to account timezone. | George Tan | Deployed in v3.1.2. Monitor for edge cases.
2026-02-19 | Billing portal returning 403 for users with legacy plan codes | Legacy plan IDs were not mapped in the new billing system migration; mapping table updated. | Fiona Walsh, Hannah Scott | ~40 users affected; all confirmed access restored.
2026-02-20 | Mobile app crash on iOS 17.3 when opening notifications drawer | Swift UI bug with NavigationStack — patched in mobile release 4.2.1, pushed to App Store. | Hannah Scott, Ivan Novak | App Store review approved within 6 hours.
2026-02-22 | SAML assertion failing for Okta-integrated enterprise client | Certificate rotation on client side caused mismatch; updated metadata XML and re-tested. | Ivan Novak | Client confirmed SSO working. Cert expiry reminder set.
2026-02-11 | CSV import rejecting files with UTF-8 BOM encoding | Added BOM stripping to file parser. | George Tan
2026-02-13 | Password reset emails going to spam for Outlook users | SPF/DKIM records updated; email headers corrected. | Fiona Walsh | Deliverability improved to 98%.
2026-02-21 | Salesforce integration sync lagging by 4–6 hours |  | Hannah Scott, Ivan Novak | Root cause still being investigated with Salesforce support.